## Summary
Change Detection — Accuracy Improvement Roadmap
Recommended approach | Hybrid: keep completed classical/infrastructure work; make Delhi-labeled evaluation the single source of truth; fine-tune AdaptFormer for domain transfer; calibrate fusion/thresholds against real IoU. Defer extended KPCAMNet and new model training until fine-tuning results are measured.
Why this wins | Prior integration (KPCA, IR-MAD, GSD, benchmark harness) improved machinery and regression safety, but LEVIR-CD tiles do not represent Delhi imagery. Domain mismatch remains the dominant accuracy gap. Labeled Delhi pairs + transfer learning addresses the root cause; grid-search calibration is fast, measurable, and complements both.
Non-negotiable first step | Build a Delhi evaluation set (20–40 pairs minimum to start; grow to 100–300 for fine-tuning). Without it, no improvement can be verified.
Highest expected payoff | Fine-tune AdaptFormer on Delhi imagery (GPU, 1–2 weeks engineering + labeling time).
Explicitly deprioritize | Siamese U-Net from scratch (needs 1000+ labeled pairs). Extended KPCAMNet only if unsupervised fallback is required.
Target success metrics | Delhi eval mean F1 ≥ 0.55 (phase 1 baseline target); ≥ 0.65 after calibration; ≥ 0.70 after fine-tuning. Car-FP synthetic gate stays F1 = 1.0 (no regression).
Total timeline (estimate) | 1.5-2 weeks end-to-end: 2-3 days eval + calibration, 5-7 days labeling expansion + fine-tune, 2-3 days integration + validation.

## Approach Comparison
Topic | Prior Plan (SRCDNet/KPCAMNet/CD-Review) | Found Plan (Delhi-focused) | Assessment | Combined Decision
Evaluation data | LEVIR-CD sample tiles + synthetic cases | 20–40 Delhi pairs with hand-drawn masks | LEVIR useful for regression; useless as Delhi proxy | Keep LEVIR/synthetic as CI gates; Delhi set = primary metric
Domain adaptation | Not addressed (pretrained AdaptFormer only) | Fine-tune AdaptFormer on Delhi (transfer learning) | Biggest gap for your imagery | P0: build fine-tuning pipeline + Delhi weights
Threshold / fusion tuning | Manual env flags + validation gates | Grid-search sensitivity/fusion/KPCA params on real IoU | Fast, no training, immediate gain | P0: add compare_methods.py + calibration script
KPCAMNet / KPCA | Implemented basic KPCA + polar analysis | Extend multi-channel KPCA (lower priority) | Helped Feature-Based (F1 0.12→0.32 on LEVIR); not AI-path fix | Keep current KPCA; extend only if unsupervised path needed (P2)
IR-MAD | Implemented channel + optional regression norm | Not emphasized | Regression norm hurt F1; channel neutral on Delhi gate | Keep channel opt-in; skip default regression norm
GSD harmonization | Implemented for mismatched GeoTIFF GSD | Not mentioned | Prevents false texture diffs on mixed-resolution pairs | Keep enabled (already done)
BIT_CD ensemble | Optional second DL model | Not mentioned | Needs weights; payoff unproven on Delhi | Defer until after AdaptFormer fine-tune (P3)
Siamese U-Net training | Explicitly skipped | Not recommended near-term | Agree — data-hungry | Skip unless 1000+ labeled pairs available
Car / transient FP guard | Synthetic parked_cars benchmark case | Not mentioned | Critical for Delhi road imagery | Keep as mandatory regression gate
Verdict: Found plan correctly identifies the bottleneck (domain + measurement). Prior plan correctly built reusable infrastructure. Combined roadmap = Delhi eval first → calibrate → fine-tune → integrate.

## Implementation Plan
Phase | Priority | Workstream | Task | Description | Depends On | Effort | Owner | Deliverable | Success Criteria | Status
0 | Done | Foundation | Benchmark harness | validate_detection.py: synthetic + LEVIR-CD + kappa + car-FP gate | — | Done | Eng | scripts/validate_detection.py | All unit checks pass; synthetic F1 stable | Complete
0 | Done | Foundation | Classical channels | KPCA (feature path), IR-MAD (opt-in), GSD harmonization, BIT_CD scaffold | — | Done | Eng | app/cd_models/*, detection_engine.py | No car-FP regression; infra ready | Complete
1 | P0 | Evaluation | Curate Delhi image pairs | Select 20–40 representative before/after pairs from library (building, road, open land, mixed GSD). Document pair metadata (date, GSD, zone). | — | 2–4 days | Domain + Eng | docs/delhi_eval/manifest.json | ≥20 pairs covering main change types | Not started
1 | P0 | Evaluation | Create ground-truth masks | Hand-label binary change masks in QGIS or LabelMe (rough polygons OK). One mask per pair, same resolution as detection input. | Curate Delhi pairs | 2–4 days | Domain | docs/delhi_eval/labels/*.png | Every pair has aligned GT mask | Not started
1 | P0 | Evaluation | Wire Delhi eval into harness | Extend validate_detection.py --real to load docs/delhi_eval/; report per-pair and mean IoU/F1/kappa; save comparison PNGs. | GT masks | 0.5 day | Eng | Updated validate_detection.py | Baseline Delhi metrics recorded | Not started
1 | P0 | Evaluation | Record baseline report | Run AI-Based DL + Feature-Based + Hybrid at default settings; store metrics.json as baseline for all future A/B tests. | Delhi eval wired | 0.5 day | Eng | runs/delhi_baseline/ | Baseline F1 documented per method | Not started
2 | P0 | Calibration | Build compare_methods.py | New script: sweep methods, fusion modes, sensitivity, DETECTION_* flags; output ranked CSV/JSON vs Delhi GT. | Delhi eval | 1 day | Eng | scripts/compare_methods.py | Single command produces method leaderboard | Not started
2 | P0 | Calibration | Grid-search fusion thresholds | Search smart_union floors, hysteresis high/low, classical percentile q, DL threshold, KPCA on/off for score map. | compare_methods.py | 1–2 days | Eng | runs/calibration/best_params.json | Measurable F1 lift ≥5% vs baseline | Not started
2 | P0 | Calibration | Promote winning defaults | Apply calibrated params as new defaults only where Delhi F1 improves and car-FP gate unchanged. | Grid-search | 0.5 day | Eng | detection_config.py / constants | Delhi mean F1 up; parked_cars F1=1.0 | Not started
3 | P1 | Transfer learning | Expand labeled set for training | Grow Delhi labels to 100–300 pairs (semi-automated pre-label + human fix). Split train/val/test (70/15/15). | Initial 20–40 pairs | 1–2 weeks | Domain | data/delhi_cd/train¦val¦test | ≥100 train pairs with masks | Not started
3 | P1 | Transfer learning | Fine-tuning script | scripts/finetune_adaptformer.py: load HF checkpoint, train on Delhi tiles, early-stop on val F1, export best weights. | Expanded labels | 2–3 days | Eng | scripts/finetune_adaptformer.py | Reproducible train run from CLI | Not started
3 | P1 | Transfer learning | GPU training run | Rent cloud GPU (A10/T4); train 20–50 epochs on 256px crops; log metrics. | Fine-tuning script | 4–8 hours GPU | Eng | models/adaptformer_delhi/ | Val F1 beats pretrained on Delhi | Not started
3 | P1 | Transfer learning | Integrate Delhi weights | model_inference.py: load local fine-tuned weights when present (ADAPTFORMER_WEIGHTS env); fallback to HF LEVIR model. | GPU run | 1 day | Eng | app/model_inference.py | App uses Delhi model by default locally | Not started
4 | P2 | Optional DL | BIT_CD ensemble A/B | Only if fine-tuned AdaptFormer still misses specific change types; benchmark ensemble on Delhi eval before enabling. | Phase 3 complete | 2 days | Eng | DETECTION_ENSEMBLE gate | Delhi F1 gain ≥2% vs fine-tuned alone | Deferred
4 | P2 | Optional classical | Extended KPCAMNet | Multi-channel stacked KPCA, more components, domain-specific patch sizes. For unsupervised / no-GPU fallback only. | Phase 2 complete | 3–5 days | Eng | app/cd_models/kpca_features.py | Feature-Based Delhi F1 improves; AI path unaffected | Deferred
5 | P3 | Not planned | Siamese U-Net from scratch | Requires 1000+ labeled pairs; unlikely to beat fine-tuned AdaptFormer. | — | — | — | — | Skip unless data scale changes | Skipped
6 | P1 | Production | Re-run full validation gates | Delhi eval + synthetic + car-FP + LEVIR regression after each promoted change. | Phases 2–3 | 0.5 day | Eng | runs/final_validation/ | All gates pass; metrics in README/docs | Not started
6 | P1 | Production | Update docs & .env.example | Document Delhi eval workflow, fine-tuned weights path, calibration commands. | Validation | 0.5 day | Eng | DEV_SETUP.md, .env.example | Team can reproduce benchmark end-to-end | Not started

## Timeline
Week | Focus | Key outputs | Gate / decision point
Week 1 | Delhi eval set + baseline | 20–40 labeled pairs; baseline metrics; compare_methods.py started | Go/no-go: enough pairs to measure (≥20)
Week 2 | Calibration | Grid-search complete; promoted defaults; compare_methods leaderboard | Go/no-go: ≥5% F1 lift or proceed to fine-tune anyway
Week 2–4 | Label expansion + fine-tune | 100–300 pairs; GPU training; Delhi AdaptFormer weights | Go/no-go: val F1 beats pretrained
Week 4–5 | Integration + validation | App loads Delhi weights; final gates; documentation | Release calibrated + fine-tuned pipeline
Week 5+ (optional) | KPCAMNet / BIT_CD | Only if fine-tuned model still insufficient | Each optional item needs Delhi F1 proof

## Risks & Dependencies
Risk | Impact | Mitigation | Owner
Insufficient labeled Delhi data | Fine-tune underperforms | Start with 20–40 for calibration; grow to 100+ before GPU spend | Domain team
Label inconsistency (rough polygons) | Noisy F1, wrong tuning | Labeling guide; double-review 10% of masks; focus on building/road changes | Domain team
CPU-only inference too slow | Poor UX on large GeoTIFFs | Keep 4096 cap; optional DETECTION_TTA=off; queue jobs with progress | Eng
GPU cost / access | Blocks fine-tuning | Single 4–8h cloud session; small tile dataset sufficient | Eng
Over-tuning on small eval set | Overfits calibration | Hold out 20% test pairs never used in grid-search | Eng
Car false positives return | User trust loss | Mandatory parked_cars synthetic gate before any default change | Eng